## Sprint_1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 11.03.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Github Repository erstellen | 1 | 0.3 | -0.7 | x |  | https://github.com/Alaskiara/FlashLearn
2 | Trello Board erstellen | 1 | 0.5 | -0.5 | x |  | https://trello.com/b/c7ez7kFl/flashlearn
3 | HTML-Grundstruktur erstellen | 1 | 1 | -1 | x
-1
1
3
0
0
0
0
|  |  |  | 0.8 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_2
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 11.03.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
4 | Benutzeroberfläche verfeinern | 2 | 3 | 1 | x
5 | Datenbankstruktur entwerfern | 2 | 3 | 1 | x
6 | Erstellen von Flashcards | 2 | 2.5 | -1 | x
7 | Bearbeiten von Flashcards | 2 |  | -1 |  | x
1
3
0
0
0
0
|  |  |  | 4 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_3
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 03.04.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
7 | Bearbeiten von Flashcards | 2 | 4 | 2 | x
8 | Flashcards speichern | 2 | 4 | 2 | x
9 | Show/Hide Button | 2 | 3 | 1 | x
10 | Benutzer-Login |  |  | 0
11 | Löschen von Flashcards | 2 | 3 | 1 | x
0
0
0
0
0
|  |  |  | 6 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_4
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 21.04.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
12 | Benutzeroberfläche anpassen | 4 | 3 | -1 | x
| (Show/Hide, Delete, Edit, ...) |  |  | 0
15 | Benutzer registrieren | 4 | 3 | -1 | x
10 | Benutzer Login | 2 | 3 | 1 | x
0
0
0
0
0
0
|  |  |  | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_5
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 13.05.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
13 | Show Last/Show All Button | 3 | 5 | 2 | x |  | Button um alle Flashkarten anzuzeigen
|  |  |  | 0 |  |  | (Show All) / zuletzt-hinzugefügte
|  |  |  | 0 |  |  | Flashkarte anzeigen (Show Last)
14 | Previous/Next Button | 2 | 5 | 3 | x
15 | Testkategorie | 2 | 4 | 2 | x |  | Für Tests eine Kategorie mit 10 Fragen
16 | Punktesystem | 3 | 2 | -1 |  | x | System für beantwortete Fragen
17 | Leaderboard | 3 | 5 | 2 | x |  | Leaderboard mit User, Kategorie und Score
18 | Change password | 2 | 2 | 0 | x |  | Benutzerpasswort ändern
0
0
|  |  |  | 8 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_6
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 20.05.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias, Silvia
Participant 5 |  | Wucher, Daniel
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
19 | Timer | 3 |  | -3 |  | x
20 | Kategorie auswählen | 5 |  | -5 |  |  | Auswählen und durchgehen einer
21 | Testlauf | 4 |  | -4 |  |  | Kategorie mit Punkte abspeichern
22 | Fehlerbehebung | 2 | 3 | 1 | x
23 | Flashcards aus DB anzeigen lassen | 5 | 8 | 3 | x
24 | Add Flashcard in DB speichern | 3 | 5 | 2 | x
25 | Edit Flashcard in DB speichern | 3 | 5 | 2 | x
26 | Delete Flashcard in DB speichern | 2 | 5 | 3 | x
27 | Show Button Fehlerbehebung | 2 | 5 | 3 | x
0
|  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol

## Sprint_7
Sprint Review Protocol
Sprint No: |  | 7
Date & Time |  | 29.06.2025
Group Number |  | 11
Participant 1 |  | Strobl, Laurin
Participant 2 |  | Brezina, Luca
Participant 3 |  | Geischläger, Nina
Participant 4 |  | Ortiz Arias,Silvia
Participant 5
Mentor |  | Lena Esther Oswald
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
28 | Welcome Message hinzugefügt | 1 | 0.5 | -0.5 | x
29 | "Add Flashcard"-Button ist nur mehr | 1 | 0.5 | -0.5 | x
| für eingeloggte User zu sehen |  |  | 0
30 | Extra Link zur Login Page hinzugefügt | 0.5 | 0.2 | -0.3 | x
31 | Autovervollständigung für Login- | 0.5 | 0.2 | -0.3 | x
| Form deaktiviert |  |  | 0
32 | Autovervollständigung für Sign Up- | 0.5 | 0.2 | -0.3 | x
| Form deaktiviert |  |  | 0
33 | Login/Sign Up Button ausgeblendet, | 0.5 | 0.2 | -0.3 | x
| wenn man sich bereits auf Login/Sign |  |  | 0
| Up Form befindet |  |  | 0
34 | Fehlerbehebung "Show Last/Show | 1 | 1 | 0
| All"-Button |  |  | 0
35 | Fehlerbehebung "Next/Previous"- | 1 | 2 | 1
| Buttons |  |  | 0
36 | Übersetzungen ausgebessert | 0.1 | 0.1 | 0
37 | "Add Category"-Button und | 3 | 5 | 2 |  |  | kategorie.php, delete_category.php,
| Funktionalitäten hinzugefügt; |  |  | 0 |  |  | save_category.php hinzugefügt
| "Delete Category"-Button |  |  | 0
| hinzugefügt |  |  | 0
38 | Fehlerbehebungen | 3 | 5 | 2 | x |  | Kategorieansicht nach Löschen und
|  |  |  | 0 |  |  | Schließen von Flashcard bleibt;
|  |  |  | 0 |  |  | Kategoriecounter funktioniert;
|  |  |  | 0 |  |  | "Save"-Button funktioniert wieder
39 | Fehlerbehebung | 2 | 2 | 0 | x |  | Kategorieansicht nach Speichern von
|  |  |  | 0 |  |  | Flashcard bleibt
40 | Fehlerbehebung | 1 | 1 | 0 | x |  | "Add Category"-Button funktioniert
|  |  |  | 0 |  |  | wieder
41 | Fehlerbehebung | 1 | 1 | 0 | x |  | nach Speichern/Bearbeiten einer
|  |  |  | 0 |  |  | Flashcard bleiben Karten der
|  |  |  | 0 |  |  | entsprechenden Kategorie angezeigt
42 | Fehlerbehebung | 1.5 | 1.5 | 0 | x |  | Js-Datei wurde nach Login nicht mehr
|  |  |  | 0 |  |  | eingebunden, Fehler lag in
|  |  |  | 0 |  |  | Kategorie.php
43 | Datenbank-Fehler ausgebessert | 1 | 1 | 0 | x
44 | Artefacts Ordner angelegt und angefangen | 1 | 1 | 0 | x
45 | Styling angepasst | 1 | 1 | 0 | x |  | Login/Sign Up/Logout-Button und
|  |  |  | 0 |  |  | Header angepasst
46 | Fehlerbehebung | 1 | 1 | 0 | x |  | close Flashcard --> zurück zur
|  |  |  | 0 |  |  | Kategorieansicht
47 | redundanten Code entfernt | 0.5 | 0.5 | 0 | x
48 | Change Password-Interface implementiert | 2 | 2 | 0 | x
49 | Erstellung des Logobildes (ohne KI) | 1 | 1.5 | -0.3 | x |  | Erstellung des Logobildes (ohne KI)
und Einfügen in den Header
|  |  |  | 2.8 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol